## CapEx Budget
CapEx Budget & Tracker
Line-item budget vs. actuals across the renovation program
PROJECT PARAMETERS
| Unit Count | 200
| Total Budget / Unit | 33086.1
| Actual Spend / Unit | 17220
| Line Item | Budget | Actual | Variance | Var % | Completion % | Vendor | Status | Notes
— INTERIOR RENOVATION —
| Flooring (LVP) | 600000 | 300000 | -300000 | -50% | 50% | ABC Flooring | In Progress
| Cabinets & Countertops | 400000 | 180000 | -220000 | -55% | 45% | KitchenPro | In Progress
| Paint & Finishes | 200000 | 95000 | -105000 | -52.5% | 47.5% | Sherwin | In Progress
| Lighting Package | 80000 | 40000 | -40000 | -50% | 50% | LightCo | In Progress
| Plumbing Fixtures | 120000 | 55000 | -65000 | -54.17% | 45.83% | FlowPro | In Progress
| Appliances | 300000 | 140000 | -160000 | -53.33% | 46.67% | GE Supply | In Progress
— EXTERIOR —
| Roof Repairs | 350000 | 350000 | 0 | 0% | 100% | RoofMax | Complete
| Paint / Siding | 220000 | 110000 | -110000 | -50% | 50% | Painters LLC | In Progress
| Parking Lot Seal & Stripe | 80000 | 80000 | 0 | 0% | 100% | AsphaltCo | Complete
| Landscaping Overhaul | 60000 | 25000 | -35000 | -58.33% | 41.67% | GreenScape | In Progress
— AMENITIES —
| Pool Deck Renovation | 90000 | 60000 | -30000 | -33.33% | 66.67% | PoolMasters | In Progress
| Clubhouse Refresh | 120000 | 40000 | -80000 | -66.67% | 33.33% | Interior Design Co | In Progress
| Fitness Center Equipment | 50000 | 50000 | 0 | 0% | 100% | FitnessCo | Complete
| Dog Park / Playground | 30000 | 0 | -30000 | -100% | 0% | TBD | Not Started
— SYSTEMS —
| HVAC Replacements (partial) | 200000 | 120000 | -80000 | -40% | 60% | HVACPro | In Progress
| Electrical Upgrades | 60000 | 30000 | -30000 | -50% | 50% | ElectricCo | In Progress
— CONTINGENCY & SOFT —
| Contingency (10%) | 240000 | 0 | -240000 | -100% | 0% | — | Not Started
| Permits & Fees | 20000 | 12000 | -8000 | -40% | 60% | — | In Progress
| Construction Management | 80000 | 35000 | -45000 | -56.25% | 43.75% | CM Co | In Progress
| PROGRAM TOTALS | 3300000 | 1722000 | -1578000 | -47.82% | 52.18%
Per Unit Metrics
| Budget / Unit | 16500
| Actual / Unit | 8610
| Variance / Unit | -7890
Private & Confidential · Rescia Properties, LLC · © 2026 · For single-user program use only